| Milestones Instructions: Mark month(s) with an X to show when each item is to be complete or use/modify sample timeline. |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Development Team | Identify development team members |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Set up regular meetings with Course Development Team (CDT) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Notify CDT of CAFE workshops dates or schedule alternate workshops with CAFE |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources | Review Program of Study and CVS Application |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Order textbooks for Course Development Team |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify specialized space or lab space needs and forward to MRP |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review existing courses to be included in new courses/program |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify existing resources or equipment to be included in new program |  |  |  |  |  |  |  |  |  |  |  |  |
| Curriculum | Develop draft Course Learning Outcomes for new program (this should be done with entire Development Team) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Delegate to CDT members who is to revise existing and create new course outlines using draft Course Learning Outcomes for new program |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Discuss with CDT members the required elements for CO and refer to Curriculum Specialists (as needed): - Description - Rationale - Course Specific Learning Outcomes - EESO - Framework for evaluation and weighting linked to LO and EESO - Sequence of Instruction - Required Textbook/Resources |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Determine co and pre-requisites |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalize course descriptions and forward to... |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify 3 General Education courses for 2 or 3 year programs (note: these courses must be approved by Gen Ed Committee prior to finalizing Program of Study) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Meet with CAFE education and multimedia staff for hybrid courses or learning object development (if needed) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review Course Outlines with CAFE staff prior to finalizing |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalize and Submit Course Outlines |  |  |  |  |  |  |  |  |  |  |  |  |
| Space Consultation | Contact other program teams regarding sharing space, equipment or other resources |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contact Central Scheduling regarding timetable (note: submit any special requests a minimum of 6 months prior to course start) |  |  |  |  |  |  |  |  |  |  |  |  |
| Other | Develop Program Guide |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Arrange Field Placements |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Submit Textbooks order to Bookstore |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establish Program policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establish Program Advisory Committee |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Determine which courses are eligible for PLAR |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Arrange Guest speakers/Field Trips |  |  |  |  |  |  |  |  |  |  |  |  |